## Validation Plan
List of the Pre-ACCEPTANCE CRITERIA
| Part name: | 77GHz Radar |  | Reason for release | x | New Product. New Equipment.
| Production line(s): | Radar LineNum |  |  | o | Product Software modification (no comp change, E²prom change)
| Date: | yyyy/mm/dd |  |  | o | Hardware Modification (without hardware tool modifications, new family,...)
| Station | Sensor Test |  |  | o | New Machine / Line Modification, product transfert(without change), production break > 1 year
1 | P | Plan
2 | OK | Done : results OK
3 | NOK | Done : results not OK
ACTION |  |  | Result | LEADER | Action Needed | Comments
General
Equipment is able to build all part variants outlined in Egineering Specification? |  |  | OK | TestEngineer | NO | Yes, Following Sensor Test Spec E2763048
test sequences(including test limits) for each variant meet ES setup |  |  | OK | TestEngineer | NO | Yes, Following Sensor Test Spec E2763048
Equipment meets required cycletime target: within 20s |  |  | OK | TestEngineer | NO | Yes, testers achieved C\T 20s
Correct reject handling |  |  | OK | TestEngineer | NO | Confirmed
System meets ESD requirements |  |  | OK | TestEngineer | NO | Confirmed by Quality
Safety
All pneumatic and electrical joints are lockable and mounted at the proper distance from the ground? |  |  | OK | TestEngineer | NO | Yes, confirmed
Ensure there is enough space to perform the necessary changeovers in an ergonomic fashion. |  |  | OK | TestEngineer | NO | Easily change over
All E-Stops, door interlocks and light curtains are functional |  |  | OK | TestEngineer | NO | Yes, confirmed
All potential pinch points are protected with guarding |  |  | OK | TestEngineer | NO | Yes, confirmed
Changeover fixture is < 15Kg. |  |  | OK | TestEngineer | NO | Adaptor easily change over
Hardware
All connections labeled |  |  | OK | TestEngineer | NO | Yes, confirmed
All wires and cables properly routed and secured |  |  | OK | TestEngineer | NO | Yes, confirmed
Station Labelled with Name |  |  | OK | TestEngineer | NO | Yes, confirmed
Use flexible wires for moving parts of the fixture |  |  | OK | TestEngineer | NO | Yes, confirmed
Tester has an Ethernet port |  |  | OK | TestEngineer | NO | Yes, confirmed
Front Door engages and disengages automatically. Pneumatically controlled. |  |  | OK | TestEngineer | NO | Yes, confirmed
Emergency stop button |  |  | OK | TestEngineer | NO | Confirmed and Functional
Reject bin holds up to 3 UUTs |  |  | OK | TestEngineer | NO | Yes, confirmed
Failed nest does not start new test if failed unit is not placed into the reject bin |  |  | OK | TestEngineer | NO | Yes, confirmed
Once reject bin is full, the tester stops to allow further testing in the failed nest until the bin is emptied. |  |  | OK | TestEngineer | NO | Yes, confirmed
Tester cooling adequate . |  |  | OK | TestEngineer | NO | Has two fans backend
Station Labelled with Name & Serial Number |  |  | OK | TestEngineer | NO | Yes, confirmed
Software
Fixture ID Pokayoke |  |  | OK | TestEngineer | NO | Yes, confirmed
Indicates a nest is available for loading |  |  | OK | TestEngineer | NO | Yes, confirmed
Verifies a loaded part is ready for test |  |  | OK | TestEngineer | NO | Yes, confirmed
Indicates a test in progress |  |  | OK | TestEngineer | NO | Yes, confirmed
Indicates test result (which test fails) |  |  | OK | TestEngineer | NO | Yes, confirmed
Test result not lost until unit removed |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays test time |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays idle time |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays long term counter |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays short term counter |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays test sequence name, Manu number |  |  | OK | TestEngineer | NO | Yes, confirmed
Displays test step results while executing |  |  | OK | TestEngineer | NO | Yes, confirmed
Display sensor type |  |  | OK | TestEngineer | NO | Yes, confirmed
Can view tester I/O status |  |  | OK | TestEngineer | NO | Yes, confirmed
Can view tester relays status |  |  | OK | TestEngineer | NO | Yes, confirmed
CSV test result log file (all results) |  |  | OK | TestEngineer | NO | Yes, confirmed
Test software sends all test results to iTAC, not just overall pass/fail. |  |  | OK | TestEngineer | NO | Yes, confirmed
The Production interface has a drop-down menu of Manu numbers. The program asks the user to select the product variant that will be tested from the menu |  |  | OK | TestEngineer | NO | Yes, confirmed
The Production interface displays operator instructions. |  |  | OK | TestEngineer | NO | Yes, confirmed
All test results are logged locally. |  |  | OK | TestEngineer | NO | Yes, confirmed
csv data log files record SN, date/time, tester#, test time, test duration, and test result for each test |  |  | OK | TestEngineer | NO | Yes, confirmed
Documentation
Manuals (hard and soft copies) |  |  | OK | TestEngineer | NO | Softcopy and hardcopy
Schematics (hard and soft copies) |  |  | OK | TestEngineer | NO | Softcopy and hardcopy
Recommended spare parts list |  |  | OK | TestEngineer | NO | Softcopy
Source code (soft copy) |  |  | OK | TestEngineer | NO | Lab Windows CVI and Teststand, back up on CN01-mes08 server
Mechanical Drawings |  |  | OK | TestEngineer | NO | Softcopy
Recommended preventative maintenance plan |  |  | OK | TestEngineer | NO | Softcopy