## Validation Plan
List of the ACCEPTANCE CRITERIA For Radar04 SEL
| Part name: | Radar 5 SEL |  | Reason for release | x | New Product. New Equipment.
| Production line(s): | Radar05 |  |  | o | Product Software modification (no comp change, E²prom change)
| Date: | 2022-11-29 |  |  | o | Hardware Modification (without hardware tool modifications, new family,...)
[5 empty] | o | New Machine / Line Modification, product transfert(without change), production break > 1 year
1 | P | Plan
2 | OK | Done : results OK
3 | NOK | Done : results not OK
ACTION |  |  | Result | LEADER | Action Needed | Comments
General
Equipment is able to build all part variants outlined in Egineering Specification? |  |  | OK | Shaloc Zhang | NO | Yes,
test sequences(including test limits) for each variant meet ES setup |  |  | OK | Shaloc Zhang | NO | Yes, Following Spec.
Equipment meets required cycletime target: within 12s |  |  | OK | Shaloc Zhang | NO | Yes, SWL/EOL fixture can reached the CT target
Correct reject handling |  |  | OK | Shaloc Zhang | NO | Yes, Robot will place the failure module into reject chute.
Mapping between fixture nest and test software is correct. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
The 8 SWL fixutres are capable of programming 8 UUTs independently and in parallel through CAN |  |  | OK | Shaloc Zhang | NO | Yes, All pneuamtic connectors are able to engage and test independently
The 2 EOL fixutres are capable of Testing 2 UUTs independently and in parallel through CAN |  |  | OK | Shaloc Zhang | NO | Yes, All pneuamtic connectors are able to engage and test independently
System meets ESD requirements |  |  | OK | Shaloc Zhang | NO | Confirmed by Linda
Safety
All pneumatic and electrical joints are lockable and mounted at the proper distance from the ground? |  |  | OK | Shaloc Zhang | NO | Yes, All pneumatic parts (cylinder, valve, manifold, etc) are mounted on SEL system.
Ensure there is enough space to perform the necessary changeovers in an ergonomic fashion. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
All E-Stops, door interlocks and light curtains are functional |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
All potential pinch points are protected with guarding |  |  | OK | Shaloc Zhang | NO | Yes, Connectors are guarded with fixture plate
Changeover fixture is < 15Kg. |  |  | OK | Shaloc Zhang | NO | Yes, Fixture easily change over
Hardware
All connections labeled |  |  | OK | Shaloc Zhang | NO | Yes, lables on all connections
All wires and cables properly routed and secured |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Station Labelled with Name |  |  | OK | Shaloc Zhang | NO | Yes, Station with the nameplate
Use flexible wires for moving parts of the fixture |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Interchangeable fixtures |  |  | OK | Shaloc Zhang | NO | Yes, it can be easy to move when change over
Tester has an Ethernet port |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
compressed air-controlled, 10-up fixture. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
module connector engages and disengages automatically. Pneumatically controlled. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
When module connector's pins need replacing, a quick disconnect is available to allow faster removal of the module connector |  |  | OK | Shaloc Zhang | NO | Yes, All DUT connectors have DB9 inteconnects and could be easily removed
Emergency stop button |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed and Functional
Reject bin holds up to 3 UUTs |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Failed nest does not start new test if failed unit is not placed into the reject bin |  |  | OK | Shaloc Zhang | NO | Yes, Robot place the failure module into reject bin if the DUT test fail.
Once reject bin is full, the tester stops to allow further tesRoger You in the failed nest until the bin is emptied. |  |  | OK | Shaloc Zhang | NO | Yes,
Part presence sensor calibrated properly. Does not engage prematurely. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Software
Parameter setup password protected? |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Indicates a nest is available for loading |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Verifies a loaded part is ready for test |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Indicates a test in progress |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Indicates test result (which test fails) |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Test result not lost until unit removed |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays test time |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays idle time |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays long term counter |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays short term counter |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays test sequence name, Vehicle number |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Displays test step results while execuRoger You |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Can read/write memory locations |  |  | OK | Shaloc Zhang | NO | Yes, CAN read/write memory tool is available
Can view tester I/O status |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Can view tester relays status |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
CSV test result log file (all results) |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Stop test on data storage failure |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Error log file |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Desplay iTAC connection / communication status: on or off |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Test software sends all test results to iTAC, not just overall pass/fail. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Compressed air pressure monitored. Test stopes if pressure too low. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Test software capable of distinguishing 77GHz 1.2, 77GHz 1.3 and 77GHz GM 1.2 fixtures. |  |  | OK | Shaloc Zhang | NO | Yes, Each fixture has unique ID that will identify if wrong fixture was loaded
csv test log file has "fail codes" column |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
The Production interface and the test software are implemented with UI for Teststand |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
The Production interface has a drop-down menu of Vehicle numbers. The program asks the user to select the product variant that will be tested from the menu |  |  | OK | Shaloc Zhang | NO | Yes, The database file will be stored locally on the PC
The Production interface displays the Vehicle number being used. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
If the selected Vehicle number and file name does not match the vehicle number and attribute from Itac server , a warning is displayed to the operator. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
All test results are logged locally. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Debug/TroubleshooRoger You interface allows the relays to be toggled |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
csv data log files record SN, date/time, tester#, test time, test duration, and test result for each test |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
New log files do not overwrite exisRoger You ones. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Troubleshoot interface: powers on a module |  |  | OK | Shaloc Zhang | NO | Yes, CAN read/write tool powers up the units and debug the functions
Troubleshoot interface: could use locally stored system/test configuration files instead of from the recipe station. |  |  | OK | Shaloc Zhang | NO | Yes, The recipe .ini files are stored on local PC and the information is extracted from there
After a failed module is removed from the nest, a new test can not start from that nest until the fail chute detected a new failed module. |  |  | OK | Shaloc Zhang | NO | Yes, Confirmed
Documentation
Manuals (hard and soft copies) |  |  | OK | Shaloc Zhang | NO | Softcopy and hardcopy, Confirmed
Schematics (hard and soft copies) |  |  | OK | Shaloc Zhang | NO | Softcopy and hardcopy, Confirmed
Recommended spare parts list |  |  | OK | Shaloc Zhang | NO | Softcopy, Confirmed by Roger You
Source code (soft copy) |  |  | OK | Shaloc Zhang | NO | Yes, Lab Windows CVI and Teststand, back up on \\CN01-MES08 server
Mechanical Drawings |  |  | OK | Shaloc Zhang | NO | Yes, 2-D mechanical drawings are avaialble on the PC
Recommended preventative maintenance plan |  |  | OK | Shaloc Zhang | NO | Yes, Softcopy, Confirmed