## Validation Plan
Acceptance Criteria for Radar 2 77GHz G1.3 Nissan VS412
| Part name: | Radar 77GHz |  | Reason for release | x | New Product. New Equipment.
| Production line(s): | Radar 2 |  |  | o | Product Software modification (no comp change, E²prom change)
| Date: | 2022-12-23 |  |  | o | Hardware Modification (without hardware tool modifications, new family,...)
[5 empty] | o | New Machine / Line Modification, product transfert(without change), production break > 1 year
1 | P | Plan
2 | OK | Done : results OK
3 | NOK | Done : results not OK
Item |  |  | Result | Leader | Action needed | Comments
General
VS412 tooling does not have risk of operator injury |  |  | OK | Jason | No | Yes, it's safety
VS412 tooling is able to build all part variants outlined in Egineering Specification? |  |  | OK | Jason | No | All 77GHz variants, and also launched yet.
VS412 tooling meets ESD requirements as outlined in Specification? |  |  | OK | Jason | No | ESD Passed,checked by Quaility
cycle time <16s |  |  | OK | Jason | No | Yes, checked by IE engineer:10.5s
Hardware&Aspect
All switches, LEDs, Attachments are functional? |  |  | OK | Jason | No | Yes, function is ok
All power connector plugs should have GND pins? |  |  | OK | Jason | No | Yes, function is ok
All wires and cables properly routed and secured |  |  | OK | Jason | No | Yes, function is ok
Nameplate wth fixture name, amount and type of test pin |  |  | OK | Jason | No | yes, nameplate is on fixture surface
Fixture does not bend over the product connector pins |  |  | OK | Jason | No | Yes, function is ok
Fixture does not damage the product connector and housing |  |  | OK | Jason | No | Yes, function is ok
Test probe can be easily changed |  |  | OK | Jason | No | Yes, function is ok
Probe compression with a suitable degree(4±2mm) |  |  | OK | Jason | No | Yes, function is ok
Fixture can be easily changed over from VS412 station |  |  | OK | Jason | No | Yes, function is ok
Function
The passed and failed indicators display result correctly when test finished |  |  | OK | Jason | No | Function is ok
The passed and failed Indicators display correctly when test in process |  |  | OK | Jason | No | Function is ok
Test result not lost until operator removes modules from fixture |  |  | OK | Jason | No | Function is ok
Indicator for barcode scanned sucessfully |  |  | OK | Jason | No | Function is ok
CAN debug interface for repairation |  |  | OK | Jason | No | VS412 station have this function, and is ok
Different part number products can not be scanned and test can not be started. |  |  | OK | Jason | No | PC SW have this function
Fixture ID Poka-yoke |  |  | OK | Jason | No | Yes, station software would check it
Traceability connection and visit |  |  | OK | Jason | No | Function is ok
Traceability Data record |  |  | OK | Jason | No | Function is ok
ECU power off status Poka-yoka |  |  | OK | Jason | No | Function is ok
All variants configuration correct |  |  | OK | Jason | No | yes, function is ok
Communication with VS412 station |  |  | OK | Jason | No | yes, function is ok
Data files/Trouble shooting
test result log file (all results) |  |  | OK | Jason | No | Recorded in local PC
log file for test failures (failures only) |  |  | OK | Jason | No | Recorded in local PC
error log file |  |  | OK | Jason | No | Recorded in local PC
can read module fault buffer |  |  | OK | Jason | No | Tester would response this information by serial com
can read detail test step and test information |  |  | OK | Jason | No | Tester would response this information by serial com
print fault label |  |  | OK | Jason | No | Function is ok
Documentation
Schematics (hard copies) |  |  | OK | Jason | No | Backup on CN01-MES08
Recommended spare parts list |  |  | OK | Jason | No | Yes, same supplier all use one list ,and backup on CN01-MES08
Relay configuration |  |  | OK | Jason | No | Yes, backup on CN01-MES08
Source code |  |  | OK | Jason | No | Supplier alreade provide the HEX file,and backup on CN01-MES08